Project Proposal to avail of the DILG Technical Assistance Project for Local Resource Institutes

DILG TA Project for LRIs Application Form

The DILG Technical Assistance Project for Local Resource Institutes (DILG TA Project for LRIs) is a small grant facility of the Department of the Interior and Local Government (DILG) developed by the Bureau of Local Government Supervision (BLGS) through the initiative of the Civil Society Organization/Peoples Participation Partnership Program (CSO/PPPP) Project Management Office. The DILG TA Project for LRIs is supported by a budget allocation under the CSO/PPPP Fund. 

Further details on the grant may be viewed in the DILG TA Project Implementation Guidelines through this link: https://tinyurl.com/DILG-TA-2022-GUIDELINES

The CSO/PPPP Portal is currently under maintenance. Kindly complete the application through this Google Form. 

For any questions or concerns, you may contact us through email at ta-cspf@csopppp.page. Kindly indicate the concern in the Subject Heading of the email. Thank you!

Email:

⃝	Option 1

Application Process

Step 1 – Access the application form and download the TA Guidelines and other documents.

Step 2 – Select your institution and fill out the application form with the correct details.

Step 3 – Upload the requested documents. The full list may be found in the TA Guidelines.

Step 4 – Review the details and files uploaded to ensure accuracy and correctness.

Step 5 – Submit the application and note the application number.

DILG TA Project for LRIs Application Form

Instructions: Kindly accomplish the form accordingly. Only eligible LRIs that have read and understood the Implementation Guidelines are allowed to proceed with the application.

Email:

Have you read the guidelines?	⃝ Yes

Find your institution. Please note that only LRIs that have CSIS engagements and have no pending requirements from the PMO are eligible to send proposals from CY 2022.

R5 – Partido State University

What are the three core principles of the grant?*

⃝ Matino, Mahusay, Maasahan

⃝ Evidence-Based, Innovative, Sustainable and Replicable

⃝ Evidence-Based, Creative, Sustainable and Replicable

DILG TA Project for LRIs Application Form

Instructions: Kindly accomplish the form accordingly. Place N/A if the item does not apply.

Project Proponent (LRI Name):	Partido State University – College of Education

Address (Please provide the full address - Street name, Barangay, Municipality, Province, Region): 				San Juan Bautista St., Goa, Camarines Sur, Region 5

Zip Code				4422

Telephone or Cellphone number:	09499872405

School email address			op@parsu.edu.ph

What year/s did your institution implement the CSIS?	2020

Name of Project Manager/ Project Leader:	MARITA S. MAGAT, Ph.D.

Designation:	 			Dean, College of Education, Professor VI

Cellphone number: 			09516759633

Email address:			marita.magat@parsu.edu.phstructions: Kindly accomplish the form accordingly. The template for the Project Activities, Budget, and Timeline may be downloaded through this link:

Project Proposal Title: 	Combating Coastal Debris through Community-based IEC Materials Developed using Participatory Approach

(under the Coastal Debris Reduction, Environmental Awareness and Management (Coastal DREAM) Program)

Proponents:			Dr. Marita S. Magat*, Janeth A. Cledera, Rey B. Cornel,

Raymond R. Estrada, Nadine M. Iraula, May C. Manla,

Type of Project: 		Capacity-building for the community in developing IEC Materials

CSIS Service Area covered: 	Environmental Management and Capacity-Building for CSOs

CSIS Results Reference (year):	2020 (PSU)

What specific LGU Effort/Project/Strategy is the proposal related to?

This project proposal is in support to the LGU’s effort/strategies for capacity-building for civil society organizations (CSOs) and other stakeholders by involving them in the development of information, education, and communication (IEC) materials through a participatory approach and also enhancing their ability to participate in the local governance.  The community-based material development will be used as one strategy to address the need for solid waste management which is one of the immediate concerns of the LGU as reflected in the Client Satisfaction Index System (CSIS) Results in 2020.  In our target LGU, the Municipality of Tigaon, the governance and response program exceeded the citizens' expectations however, all other programs were recommended to be given priority. This project proposal is designed to respond to the environmental management service area, particularly the issue of solid waste management, wherein, one of the recommendations was the organization of seminars on solid waste management by academic institutions and other concerned agencies.  This proposed project includes the conduct of said seminars.

Likewise, this project is aligned with the UN’s Sustainable Development Goals, particularly, the goal (14) to conserve and sustainably use the oceans, seas, and marine resources for sustainable development. Given that our oceans are threatened by plastic pollution (Goal 14 | Department of Economic and Social Affairs, 2022). Specifically, this project proposal aims to reduce and prevent the accumulation of coastal debris through information, education, and communication (IEC) strategies which will raise the awareness level and motivate behavioral change related to coastal debris (Debris, 2021).

Moreover, this project supports the DENR National Solid Waste Management Commission (NSWC) Resolution No. 1441 Series of 2021, re: Resolution Adopting the National Plan of Action for the Prevention, Reduction and Management of Marine Litter (NPOA-ML).  This envisioned “A Philippine free of marine litter through shared responsibility, accountability, and participatory governance” and “Zero waste to Philippine waters by 2040”.

While the LGU has been implementing strategies for ecological solid waste management, this project proposal will focus mainly on the coastal wastes observed along the shoreline and the effectiveness of using the community-based IEC in combating such coastal debris.

Target Beneficiaries

This project proposal will benefit the following:

·         LGU Tigaon – the project will serve as one of the strategies to combat the coastal debris along its coastal barangay, Huyun-huyon, Sitio Rancho.  That is, through the community-based IEC materials, the LGU will have an evidenced-based strategy that can be sustainably implemented as part of its environmental management program.

·     Civil Society Organizations – together with the LGU, the CSO and the local community will be capacitated in creating materials that they themselves can use in promoting environmental awareness and in campaigning to mitigate and prevent coastal debris.

·        Other institutions/stakeholders – the methods (capacity-building) and the products (IEC materials) could be adapted by other institutions/stakeholders for wider dissemination and utilization.

·         Local community, tourists, and visitors – this project will provide them opportunity to take part in the project that would soon improve the LGU’s client satisfaction rating in terms of environmental management.

Project Description

This project proposal is under the holistic environmental program, Coastal Debris Reduction, Environmental Awareness and Management (Coastal DREAM).

Marine debris has been a big complex issue requiring collaborative efforts of various stakeholders. There is no one strategy that fits all its complexities. Intervention at the local community level is important. The College of Education designed an environmental management program framework presenting the holistic approach to combating coastal debris. It is consisting of four components such as (1) coastal debris assessment and monitoring, (2) environmental literacy and advocacy, (3) capacity building, and (4) Clean-Up Drive and Control. Each component adopts the strategies relevant in preparing action plans for sustainability. These strategies include (A) Research and Monitoring and Project Evaluation, (B) Education and Management, (C) Financing, Resource Allocation, and Incentives, and (D) Policy Support and Enforcement.

The Coastal DREAM Program Framework is briefly shown below:

|  | COMPONENT PROJECTS |  |  |  |
| --- | --- | --- | --- | --- |
| STRATEGY | Component 1: “Bantay-Baybayin” Coastal Debris Assessment & Monitoring | Component 2: “Kwentuhang Dagat” Environmental Literacy and Advocacy | Component 3: “Paglinang ng Kakayahan sa Pangangalaga ng Kalikasan” Capacity-Building | Component 4: “Malinis na Dagat para sa Lahat” Debris Clean-Up, Prevention, and Control |
| Research, monitoring and evaluation | Conduct of Waste Analysis and Characterization Study (WACS) | Conduct of assessment on knowledge, attitudes, and practices towards coastal debris. | Conduct of needs assessment/capacity mapping | Conduct and dissemination of research related to land-based coastal debris |
| Education and Management | Installation of signages prepared through local community approach Dissemination of policies on incentives and penalties relative to coastal debris Development of marine debris monitoring mechanism Organization of bantay-dagat citizens/ volunteers | Implementation of social marketing and communication strategies using creative IEC and other media. Conduct of seminars for various sectors, e.g., fisherfolks, household representatives, students, and employed/ business personnel | Community empowerment by conducting training on the preparation of creative IEC materials. Conduct of a learning-by -doing campaign by involving the community in waste identification, proper segregation, and management. Conduct of training on producing creative materials out of recovered reusable coastal debris and household wastes. Capacity building for the local officials and community volunteers on social marketing. | Engagement of communities in the Clean-Up drive, e.g., NSTP Classes, community organizations, etc. Collaboration with the education sector on the integration in the curriculum the Coastal Debris as part of the environmental literacy skills promotion in the 21st Century. Adoption of Circular Economy as sustainable solutions to marine litter. Conduct of training/seminar and organization of street sweepers to prevent the land-based solid wastes from entering the coastal area. Collaboration with industries in promoting circular economy Establishment of partnerships with other sectors, e.g., Church in promoting project towards Caring of Creation |
| Financing, Resource Allocation, and Incentives | Provision of Trash Bins in conspicuous places Enhancement of Material Recovery Facility (MRF) Allocation of Marine Litter/Debris fund and inclusion in the LGU APP | Provision of supplies for the massive campaign and outreach programs Provision of incentives to the best participating groups Allocation of Marine Litter/Debris fund and inclusion in the LGU APP | Conduct of capacity building to enhance their technical skills e.g., on action planning or conceptualizing and implementing projects that they can access national/international funding /grant opportunities Allocation of Marine Litter/Debris fund and inclusion in the LGU APP | Promotion of efficiency of coastal clean-up drive and control by providing recognition and incentives to participating units Allocation of Marine Litter/Debris fund and inclusion in the LGU APP |
| Policy Support and Enforcement | Review of existing policies as a basis for emerging policy needs Review of prohibitions and penalties | Strengthening of local policies to include the recognition and incentives system to motivate and sustain political will | Inclusion of marine debris in the local environmental ordinance, programs, and budget | Promotion of policies to prevent the consumer-based debris from reaching the sea. |

From the program framework, the specific component project on Capacity-Building for environmental management of LGU Tigaon is hereby proposed.  This project is designed to be accomplished at the given time frame by the DILG at the target coastal area, the Sitio Rancho of Barangay Huyon-huyon.

This Capacity-Building project aims to combat coastal debris through community-based IEC materials development using participatory approach.  It has four general strategies such as (1) research, monitoring and evaluation, (2) education and management, (3) financing, resource allocation, and incentives, and (4) policy support and enforcement.

Strategy 1: Research, monitoring and evaluation

While the CSIS results has already indicated the clients’ recommendation of conducting seminars on solid waste management, this project will further identify the specific community needs and local resources through participatory research methodology.

The Coastal Waste Analysis and Characterization Study (WACS) will be performed as a mini-research to have an evidenced-based motivation to the capacity-building efforts towards a more sustainable solid waste management program of the LGU. Likewise, a needs-based assessment or capacity mapping will be done to serve as reference in the design of a specific skills development activities. This is also one way of getting-to-know the participating CSO and local community.

Strategy 2: Education and Management

Project meetings will be conducted to involve the community in the planning and implementation of the project details particularly in the implementation of the awareness seminars and training/skills development.

Strategy 3: Financing, resource allocation and incentives

Part of the capacity development is the training on the preparation of action plans and access of the funding grants opportunities.  Meanwhile, the implementation of this capacity building project will be their learning-by-doing opportunity particularly on the utilization of available resources and provision of incentives to the best outputs (creative IEC materials) and participating units, and recognition of the collaborating stakeholders.

The community involvement in producing creative outputs will be provided with financial support and incentives. Community events such as “Guhit-Dagat” (search for best printed IEC in the different categories e.g., comics, posters, signages, and leaflets/brochures), and “SeaTalk” (Search for the best Tiktok video on coastal debris, will be implemented to encourage community participation while in the process is educating already the participants and audience about coastal debris.

Strategy 4: Policy support and enforcement

Marine litter is a global concern which the local folks can take part in the solution considering that land-based activities and consumer-based wastes contribute to this problem. Coastal debris is an issue concerning everyone not only the local residents in the coastal area but also the nearby communities and various sectors.  Thus, the review and enhancement of local policy and enforcement is a significant part of this project.

This project proposal to capacitate the community and CSO with knowledge and skills relevant to the reduction and control of coastal debris will be implemented in two months (August and September 2022).  The completion of project which includes the presentation of outputs and submission of final report will be done in the following month, October 2022.

Project Objectives

General Objective:

Reduce and prevent coastal debris through the use of campaign materials developed with the involvement of different sectors in the community through a participatory approach.

Specific Objectives per Strategy

Strategy 1 - Research

- Trace the sources and destinations of coastal debris.

- Characterize the retrieved waste from shorelines.

- Identify the felt needs and resources of the local community that can be used in addressing the need to combat coastal debris.

Strategy 2 – Education and Management

- Identify the level of environmental awareness of the community before and after the utilization of IEC materials in terms of (a) coastal ecosystems, (b) benefits derived by the community from coastal ecosystems, (c) human activities that result to waste debris accumulation, (d) effects of coastal debris on the community, and (e) responsibilities of the community members in protecting and conserving coastal resources.

- Identify the attitudes of the locality in coastal debris management.

- Conduct capability building among community members in the development of campaign materials.

Strategy 3 - Financing, resource allocation and incentives

- Promote involvement and participation of the community and stakeholders in the IEC development and dissemination through recognition and provision of financial support and incentives.

- Evaluate the campaign materials developed in terms of visual appeal, language appropriateness, and content validity.

- Determine the effectiveness of the community-based IEC materials in the promotion of coastal debris clean-up and control.

- Conduct capacity building to enhance their technical skills, e.g., on action planning or conceptualizing and implementing projects that they can access national/international funding/grant opportunities.

- Allocate Marine Litter/Debris Fund and include this in the LGU Annual Procurement Plan.

Strategy 4 – Policy Support and Enforcement

- Determine existing policies adopted by the community on coastal debris management.

- Identify the community’s perceived gaps in the implementation of coastal debris management.

- Enhance policies with inclusion of marine debris in the local environmental ordinance, programs and budget.

- Promote utilization of the IEC materials by various sectors in the community and integration of coastal debris in local policies.

Project Outcomes and Benefits

Strategy 1:  	Characterization of Coastal Debris Map along the Shoreline of Sitio Rancho, Tigaon

Identified community needs and local resources that will serve as basis and can be used in addressing the coastal debris problem.

Strategy 2: 	Increased level of environmental awareness of the community

Improved positive attitudes on coastal debris management

Enhanced capabilities of community in developing creative IEC campaign materials

Strategy 3:	Capacity development of LGU in promoting community participation and involvement

Increased appreciation of and motivation to debris reduction and prevention by the community and tourists,

Positive behavioral change

Strategy 4:	Policy Recommendations to concerned LGUs

Reduced coastal debris along the shore of Sitio Rancho

Presentation of project outputs to concerned LGU and offices

Dissemination and promotion of IEC project for sustainable implementation and adoption of other concerned communities

Expected Outputs

- Coastal Debris Map along the Shoreline of Sitio Rancho, Tigaon

- Creative community based - IEC Materials using local dialect

- Validated environmental campaign materials

- Local Policy enhancement

- Project Protocol on coastal debris reduction through community-based IEC materials

References:

Debris, M. (2021). What is Marine Debris? | OR&R’s Marine Debris Program. Noaa.gov. https://marinedebris.noaa.gov/discover-marine-debris/what-marine-debris

Goal 14 | Department of Economic and Social Affairs. (2022). Un.org. https://sdgs.un.org/goals/goal14‌

National Solid Waste Management Commission Resolution Number 1441, Series of 2021

Philippines National Plan of Action for the Prevention, Reduction and Management of Marine Litter

Project Activities, Budget, and Timeline

Program: 	Coastal Debris Reduction, Environmental Awareness and Management (Coastal DREAM)

Project:	Combating Coastal Debris through Community-based IEC Materials Developed using Participatory Approach

| Project Component/ Strategy | Activities | Expected Outcomes | Amount | Expected Date of Completion |
| --- | --- | --- | --- | --- |
| Research Monitoring and Evaluation | - Tracing the sources and destinations of coastal debris. - Characterizing the retrieved waste from shorelines. - Identifying the felt needs of the local community. - Identifying the resources that can be used in addressing the community need to combat coastal debris. | Coastal Debris Map along the Shoreline of Sitio Rancho, Tigaon Needs-Based Assessment Analysis / Capacity Mapping | 25,000 | August 2022 |
| Education and Management | - Identifying the level of environmental awareness of the community before and after the utilization of IEC materials. - Identifying the attitudes of the locality in coastal debris management. - Conducting capacity building among community members and CSO in the development of creative IEC materials. | Increased environmental awareness & behavioral change (presented in the KAP Survey) Creative community based - IEC Materials using local dialect | 75,000 | August 2022 September 2022 |
| Financing, resource allocation and incentives | - Promoting the involvement and participation of the community and stakeholders in the IEC development and dissemination through recognition and provision of financial support and incentives. - Evaluating the campaign materials developed in terms of visual/audio-visual appeal, language appropriateness, and content validity. - Guhit-Dagat Contest - Sea-Talk Contest - Determining the effectiveness of the campaign materials in the promotion of coastal debris clean-up and control. | Validated IEC materials and incentivized creative outputs Reduced number of coastal debris | 80,000 | September 2022 |
| Policy Support and Enforcement | - Determine existing policies adopted by the community on coastal debris management. - Identify the community’s perceived gaps in the implementation of coastal debris management. - Promote utilization of the IEC materials by various sectors in the community and integration of coastal debris in local policies. | Utilization of community creative IEC materials by the various sectors Policy recommendations | 20,000 | September 2022 |